## Ark1
Lofthus frukt og saft |  |  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11
Start Date: 01/10/2020
Launch website |  | 11 w | bar: WEEK 1
Planning |  | 1 w
Meeting with customer | Tim | 2 d | bar: WEEK 1
Brainstorm | All | 3 d | bar: WEEK 1
Must have | All | 3 d | bar: WEEK 1
Design |  | 3 w
UX designer | Martine | 3 w | bar: WEEK 2 to WEEK 4
Articles | Stne | 2 w | bar: WEEK 3 to WEEK 4
Photography | Stine | 2 w | bar: WEEK 2 to WEEK 3
Construction |  | 6 w
Back end developer | Martin | 3 w | bar: WEEK 3 to WEEK 5
Front end developer | Tim | 4 w | bar: WEEK 4 to WEEK 7
System testing | Tim/Martin/Martine | 3 w | bar: WEEK 7 to WEEK 8
Meeting with customer | Tim | 2 d | bar: WEEK 8
Implementation |  | 4 w
Implementation | Martine/Stine | 2 w | bar: WEEK 8 to WEEK 9
System testing | L. Wasserman | 2 w | bar: WEEK 9 to WEEK 10
Handover | Tim | 3 d | bar: WEEK 11